## Daily Tracker
JavaScript Backend Roadmap — Daily Tracker
Day | Date | Topic # | Phase | Topic Name | What to do today | Status | Notes
Phase 1 — Re-activation ¦ Jun 22 → Jul 6 ¦ Milestone: Write a function from scratch without looking anything up
Day 1 | Jun 22 | #1 | Re-activation | JS intro & setup | Watch intro, install VS Code, run your first console.log | Not Started
Day 2 | Jun 23 | #2 | Re-activation | Variables | var / let / const — code 10 examples from scratch | Not Started
Day 3 | Jun 24 | #3 | Re-activation | Arithmetic operators | All operators + operator precedence practice | Not Started
Day 4 | Jun 25 | #5 | Re-activation | Type conversion | parseInt, parseFloat, String(), Boolean() — test edge cases | Not Started
Day 5 | Jun 26 | #6 | Re-activation | Constants | When to use const vs let — rewrite Day 2 examples correctly | Not Started
Day 6 | Jun 27 | #10 | Re-activation | If statements | Write 5 real-world if/else scenarios from scratch | Not Started
Day 7 | Jun 28 | — | Re-activation | Review + practice day | Rebuild everything from Days 1-6 in a blank file, no looking back | Not Started
Day 8 | Jun 29 | #17 | Re-activation | Logical operators | && ¦¦ ! — combine with if statements | Not Started
Day 9 | Jun 30 | #18 | Re-activation | Strict equality |  | Not Started
Day 10 | Jul 1 | #19 | Re-activation | While loops | Build a countdown and a number accumulator | Not Started
Day 11 | Jul 2 | #20 | Re-activation | For loops | Loop through arrays, build a multiplication table | Not Started
Day 12 | Jul 3 | #22 | Re-activation | Functions | Write 6 functions — parameters, return values, default params | Not Started
Day 13 | Jul 4 | #23 | Re-activation | Variable scope | Local vs global — intentionally break scope to understand it | Not Started
Day 14 | Jul 5 | — | Re-activation | Phase 1 milestone | Write a tip calculator: input bill + %, output tip and total — no help | Not Started
Day 15 | Jul 6 | — | Re-activation | Buffer / catch-up day | Redo anything that didn't feel solid. Rest if ahead. | Not Started
Phase 2 — Core Backend JS ¦ Jul 7 → Aug 3 ¦ Milestone: Build a CLI contact book — store, filter, and sort entries
Day 16 | Jul 7 | #25 | Core Backend | Arrays | Create, read, update arrays — push, pop, shift, unshift, splice | Not Started
Day 17 | Jul 8 | #25 | Core Backend | Arrays continued | indexOf, includes, find, findIndex — build a search function | Not Started
Day 18 | Jul 9 | #26 | Core Backend | Spread operator | Merge arrays, copy arrays, spread into functions | Not Started
Day 19 | Jul 10 | #27 | Core Backend | Rest parameters | Write functions that accept unlimited arguments | Not Started
Day 20 | Jul 11 | — | Core Backend | Review + mini project | Build an array-based to-do list: add, remove, list items | Not Started
Day 21 | Jul 12 | #30 | Core Backend | Callbacks | Write 5 functions that accept another function as argument | Not Started
Day 22 | Jul 13 | #31 | Core Backend | forEach() | Replace all your for loops with forEach — feel the difference | Not Started
Day 23 | Jul 14 | #32 | Core Backend | map() | Transform arrays — double numbers, extract names from objects | Not Started
Day 24 | Jul 15 | #33 | Core Backend | filter() | Filter arrays by condition — combine with map | Not Started
Day 25 | Jul 16 | #34 | Core Backend | reduce() | Sum, count, group — this one needs extra practice | Not Started
Day 26 | Jul 17 | — | Core Backend | Array methods review | Chain map + filter + reduce on one dataset. Rebuild without notes | Not Started
Day 27 | Jul 18 | #35 | Core Backend | Function expressions | const fn = function(){} vs function fn(){} — know the difference | Not Started
Day 28 | Jul 19 | #36 | Core Backend | Arrow functions | Rewrite all your previous functions as arrow functions | Not Started
Day 29 | Jul 20 | — | Core Backend | Buffer / catch-up day | Redo anything shaky. Practice chaining array methods. | Not Started
Day 30 | Jul 21 | #37 | Core Backend | JS Objects | Create objects, access properties, dot vs bracket notation | Not Started
Day 31 | Jul 22 | #37 | Core Backend | Objects continued | Nested objects, loop through keys, Object.keys/values/entries | Not Started
Day 32 | Jul 23 | #39 | Core Backend | Constructors | Build a Person constructor. Create 5 instances manually | Not Started
Day 33 | Jul 24 | #40 | Core Backend | Classes | Convert your constructor to a class. Add methods | Not Started
Day 34 | Jul 25 | #41 | Core Backend | Static keyword | Add static methods to your class — understand when to use them | Not Started
Day 35 | Jul 26 | #42 | Core Backend | Inheritance | Extend your Person class — Employee, Manager — add new properties | Not Started
Day 36 | Jul 27 | #43 | Core Backend | Super keyword | Call parent methods from child class — extend constructors | Not Started
Day 37 | Jul 28 | — | Core Backend | OOP review day | Build a small zoo: Animal, Dog, Cat. Use all OOP concepts | Not Started
Day 38 | Jul 29 | #51 | Core Backend | Closures | This is tricky — watch twice, then build a counter using closure | Not Started
Day 39 | Jul 30 | — | Core Backend | Buffer / catch-up day | Closures are hard. Extra day to practice if needed | Not Started
Day 40 | Jul 31 | — | Core Backend | Phase 2 project start | Start contact book: array of objects, add/remove/search contacts | Not Started
Day 41 | Aug 1 | — | Core Backend | Phase 2 project build | Add sort by name, filter by city, display formatted output | Not Started
Day 42 | Aug 2 | — | Core Backend | Phase 2 project polish | Add error handling, edge cases — what if contact doesn't exist? | Not Started
Day 43 | Aug 3 | — | Core Backend | Phase 2 milestone | Demo your contact book. Can you explain every line you wrote? | Not Started
Phase 3 — Async Mastery ¦ Aug 4 → Aug 24 ¦ Milestone: Fetch a real public API, handle errors, log clean structured output
Day 44 | Aug 4 | #56 | Async | Async code intro | Understand the call stack, event loop, synchronous vs async | Not Started
Day 45 | Aug 5 | #56 | Async | Async code practice | setTimeout experiments — predict output before running | Not Started
Day 46 | Aug 6 | #71 | Async | Promises | Create a promise manually. .then() .catch() .finally() | Not Started
Day 47 | Aug 7 | #71 | Async | Promises continued | Promise.all and Promise.race — run parallel async operations | Not Started
Day 48 | Aug 8 | — | Async | Review + practice | Convert callback-based code to promises. Feel the improvement | Not Started
Day 49 | Aug 9 | #72 | Async | Async/Await | Rewrite your promises as async/await — much cleaner syntax | Not Started
Day 50 | Aug 10 | #72 | Async | Async/Await continued | Error handling with try/catch inside async functions | Not Started
Day 51 | Aug 11 | #57 | Async | Error handling | throw, try, catch, finally — build a function that fails gracefully | Not Started
Day 52 | Aug 12 | — | Async | Async review day | Rebuild promise to async/await chain without notes | Not Started
Day 53 | Aug 13 | #73 | Async | JSON files | Read/write JSON. JSON.parse and JSON.stringify — understand both | Not Started
Day 54 | Aug 14 | #73 | Async | JSON continued | Nested JSON, loop through it, transform the structure | Not Started
Day 55 | Aug 15 | #74 | Async | Fetch API intro | Fetch from a public API (JSONPlaceholder). Log the response | Not Started
Day 56 | Aug 16 | #74 | Async | Fetch continued | Handle loading state, errors, empty responses | Not Started
Day 57 | Aug 17 | #74 | Async | Fetch with async/await | Rewrite fetch using async/await + try/catch. Best practice form | Not Started
Day 58 | Aug 18 | — | Async | Buffer / catch-up day | Async is the hardest section. Use this if you need it | Not Started
Day 59 | Aug 19 | — | Async | Phase 3 project start | Pick a real API: OpenWeather or RestCountries. Plan your output | Not Started
Day 60 | Aug 20 | — | Async | Phase 3 project build | Fetch data, parse JSON, display formatted results in terminal | Not Started
Day 61 | Aug 21 | — | Async | Phase 3 project errors | Simulate failures — bad URL, no internet. Handle all gracefully | Not Started
Day 62 | Aug 22 | — | Async | Phase 3 project polish | Clean up code, add comments, make output readable | Not Started
Day 63 | Aug 23 | — | Async | Buffer / catch-up day | Extra day if project needs more work | Not Started
Day 64 | Aug 24 | — | Async | Phase 3 milestone | Can you fetch, parse, handle errors, and display — all from memory? | Not Started

## Progress
Progress Overview
Phase | Total Days | Done | Completion
Phase 1 — Re-activation | 15 | 0 | 0% complete
Phase 2 — Core Backend JS | 28 | 0 | 0% complete
Phase 3 — Async Mastery | 21 | 0 | 0% complete
TOTAL | 64 | 0 | 0% of full roadmap complete
Rules
1. After every topic — close the video and rebuild it from scratch in a blank file.
2. Only mark Done when you can write it from memory, not just when you watched it.
3. Buffer days are real days — use them if needed, rest if you are ahead.
4. Milestone days = no new content. Only build the project.
5. Do not move to Phase 2 until the Phase 1 milestone feels easy.